# Thesis Lab 1

# Unknown currently

- Measure / check what the diameter of the sample-rings are, surface area is critical

- Doublecheck whether there is enough acetic acid and H2SO4 in the lap

- Coordinate with Lab-techs around TAN and soil pH analysis’, I ideally want to be present (perhaps even do them myself after a demonstration) as well

? What is the targeted bulk mass density of the packed samples

? Where is the soil used for the packed samples stored

? Is the system set up such that the valve number and container number always is the same, i.e. valve 15 are connected to container 15, or is there another order.

? Are ammonium carbonate and starch (used in the standards) stored in the lab, what are typical concentrations of either

? What is the volume typically used in the acid trap

? How deep is the scratch soil marks typically

? How often is the dryer chamber exchanged - is it something I should do before starting the experiment

? How much slurry is required for triplicate TAN analysis of each treatment - should we store some extra, long term

# Setup Sketch (as far as I remember)

To convert into flux, sum of the bypass and sample flow

# Description

- Cattle-slurry with packed soil and soil collected on the day of the field experiment

- 3 treatments: no acid treatment, acetic acid treatment, and sulphuric acid treatment

- 18 samples in total

- Plus 2 standards using ammonium carbonate

## Sample Names

Samples collected on field experiment day = F

Samples with packed soil = P

Standards = S (No treatment)

Untreated = U

Acetic acid = AA

Sulphuric acid = H2SO4

Ie. For example, soil sample connected to valve 18, which is untreated packed soil = 18.P.U

# Day -2: Get soil data

## ? Same for agro soil

…

## Measure Dry-mass content in field soil-samples

Attain 3 of own soil samples from storage

Same procedure for measuring DM as with fields in L32:

- Measure mass of aluminum-container

- Dump soil into container, measure container + soil

- Dry in oven for 24 hours, measure mass afterwards

- Check here whether red plastic lids can be removed easily.

## ? Also take out samples for soil pH?

# Day -1 Prepare soils, setup, and acidify slurry

Acid-trap

needs to be refilled 0.05 M H2SO4

? I think 1 L is needed

C1V1=C2V2

V2 is only unknown

V2=V1+Vwater

C2=0.05 M

If using is 95 %Wt. H2SO4:

ρsolution=1.88337 g mL-1

For 1000 mL

msolution=1883.37 g

mH2SO4=1883 g·0.95=1789.20 g

nH2SO4 =1789.20 g98.079 g mol-1=18.24molL=C1

## Packed soils

? Where is the soil stored

Sieve the soil at the biogas plant

- Break clumps of dirt left behind

- Mix with (gloved) hand afterwards

Get special stamps from Agro

Determine how much water to add

- average gravimetric water content for cattle-soil were:

ucattle=0.17gwatergsoil

uadd=ucattle-ucurrent

? How much is gsoil, the samples are packed to uniform density, but I can’t remember how much

mwater add=uadd·gsoil

As the soils are packed 4 times:

mwater, add 4=…

Use milli-Q water!

Add the water as droplets using a pipette

How much soil to add each time

Pack the soil 4 times (largest to smallest piston!):

gsoil4=…

Scrath the surface

? Between each packing, add water and disturb the surface with a fork ≈2 mm depth

Create a line in the center, then turn the sample, remember to

Set aside for next day

When packed, enclose the samples with plastic-wrap, find 9 petri dishes and store them close

Make a dummy to check if red lid is easily exchanged with petri dish

## Field soil-samples

Take own soil samples from refrigerated storage into lab, find and number 9 samples (3 untreated = U, 3 AA, 3 H2SO4)

cover these with plastic wrap and keep them in in the lab overnight so the experiment can quickly get started the next day. Find 9 petri dishes for these and store them close

## Acidify slurry

How much slurry to use:

If we use 2 g = 2 mL per sample, with 18 samples: ≥36 mL , in 3 containers

? How much extra for TAN analysis

H2SO4

? For H2SO4, if the goal is to match the same application rate as the field trial

- Measure pH before acidifying

- Add this amount while stirring, measure pH after 1 min

0.18 kgacid60.05·10-3 tslurry=2.9975·kgacidtslurry

AA

For AA, add 0.1 mL and measure pH 1 min after each time until same pH level is reached.

- Note amount of AA used, note pH-level - triplicates!

Store slurries in enclosed containers until next day.

prepare pure ammonium carbonate sample

? Where is ammonium carbonate and starch (increase viscosity) kept

? what were typical concentrations for these

Store in lab fridge

## Prepare Picarro

Start the pump, quickly check whether the flows are reasonable

Change Any Desk code into “Windtunnel”

Setup measuring-cycle for a full experiment requiring all valves, if this is not already done

# Day 1 - start of experiment, car is needed

## Start the pump and ensure stable flow

- Ensure all sample-flows are 0.225 L/min, before experimental start

- Ensure valve-shifts work as intended

- Note time-delay between picaro and actual time

## Measure pH

For all 3 types of slurries before the start of the experiment - triplicates!

## Start the experiment, prepare current sample

Approx 2-3 min before valve shift, remove plastic-wrap from current sample

Add 2 g of needed slurry as drops, in small as droplets

Exchange red plastic lid, with petri-dish

Add to Picarro setup

Note picaro-time for the shift, and the flow of the sample stream, and bypass

# Day 2-6 During experiment

Download yesterday’s raw Picarro file into own folder via Any Desk

Repeat for next day

# Day 7 End of Experiment

Note Picarro-time for the end of the experiment.

Download raw Picarro file for the final day.

Note bypass and sample flows, is expected to have a slight decrease - an average between start and end will be used.

Remove the samples from the setup, can most likely dilute and put into sink.